## Project Data
Project Name | Zero Downtime Linux Updates
Online team meeting | https://tu-berlin.zoom-x.de/j/2406759921?pwd=ahCbJqSuz3RaljImkCzVHeSgzqLg2k.1
3
Production system (if any)
Test system (if any) | ...
GitHub repository | https://github.com/amosproj/amos2026ss01-zero-downtime-linux-updates
GitHub feature board | https://github.com/orgs/amosproj/projects/97
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/101
Position of T-shirt logo | Upper Torso Right Small
Link to logo for black T-shirt | https://github.com/amosproj/amos2026ss01-zero-downtime-linux-updates/blob/main/Deliverables/sprint-01/team-logo.svg
Link to logo for white T-shirt | https://github.com/amosproj/amos2026ss01-zero-downtime-linux-updates/blob/main/Deliverables/sprint-01/team-logo.svg
Additional materials | https://discord.gg/cBnpkJKNEu
Team maling list | oss-amos-proj1@lists.fau.de
Happines Index | https://happy.uni1.de/login
Planning Poker | https://planningpokeronline.com/t2YLAtlYDVOOcjJW6gzq/

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Auer | Katharina | KathiAurina | katharina.auer@fau.de
Böhm | Luca | QW3RAT | luca.boehm@fau.de
Durand | Patrick | patridu | patrick.durand@fau.de
Freymann | Jaroslav | IFrey | jaroslav.freymann@fu-berlin.de
Friedrich | Jeremias | Jerry1098 | jeremias.friedrich@fau.de
Klem | Luca | Lugga19 | luca.klem@fau.de
Meusling | Patrick | SirGankalot | meusling@campus.tu-berlin.de
Reinel | Moritz | moritz-reinel | mo.ritz@fau.de
Schütz | Julian | Beambamacrys | julian.schuetz@fau.de
Zobel | Simeon | uzantome | git@uzanto.me

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
1 | 2026-04-15 | Böhm | Klem | Everyone else | N/A | Patrick Meusling
2 | 2026-04-22 | Klem | Böhm | Everyone else | Jeremias Friedrich | Patrick Meusling
3 | 2026-04-29 | Böhm | Klem | Everyone else | Julian Schütz | Patrick Meusling
4 | 2026-05-06 | Klem | Böhm | Everyone else | Katharina Auer | Patrick Meusling
5 | 2026-05-13 | Böhm | Klem | Everyone else | Moritz Reinel | Patrick Meusling
6 | 2026-05-20 | Klem | Böhm | ... | Katharina Auer | Patrick Meusling
7 | 2026-05-27 | Böhm | Klem |  | Jaroslav Freymann | Patrick Meusling | Mid-term due
8 | 2026-06-03 | Klem | Böhm |  | Patrick Durand | Patrick Meusling
9 | 2026-06-10 | Böhm | Klem |  | Moritz Reinel | Patrick Meusling
10 | 2026-06-17 | Klem | Böhm |  | Patrick Durand | Patrick Meusling
11 | 2026-06-24 | Böhm | Klem |  | Julian Schütz | Patrick Meusling
12 | 2026-07-01 | Klem | Böhm |  | Jeremias Friedrich | Patrick Meusling
13 | 2026-07-08 | Böhm | Klem |  | Jaroslav Freymann | Patrick Meusling
14 | 2026-07-15 | Klem | Böhm |  | Simeon Zobel | Patrick Meusling | Demo day!
15 | 2026-07-22 | Böhm | Klem |  | Simeon Zobel | Patrick Meusling | Retrospective
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here

## Team Contract
Goals | Aquire new skills
Produce a functioning and valuable product
Meeting norms | We show up on time
Devs make sure to try to understand the new sprints tickets before the team meeting
POs provide a summary of industry partner meeting
Working norms | Clean, testable code with clear commit messages, code comments
We respect other people's work
PRs must be ready for review by Tuesday 6:00 am. Tuesdays are reserved for review and merging
Coordination norms | Separate branches for issues, branches only get merged via Merge Requests, second person to review
We balance workload among the team
Communication norms | We regularly check the corresponding channels
We make sure to communicate possible problems as early as possible (absence, etc.)
We communicate constructively
Consideration norms | We discuss issues openly
We vote in case we can't reach a consensus
Cont. improvement norms | We encourage critique and improvement efforts
We reach out for help early enough to still finish our tasks
Rewards | Favorite Drink
Wear a cool hat or glasses during meetings
Sanctions | Publish a stackoverflow answer
Signatures
Scrum Master | Patrick Meusling
Product owner | Luca Klem
Product owner | Luca Böhm
Software developer | Katharina Auer
Software developer | Jaroslav Freymann
Software developer | Julian Schütz
Software developer | Patrick Durand
Software developer | Moritz Reinel
Software developer | Simeon Zobel
Software developer | Jeremias Friedrich

## Product Goal
Product Vision | Project Mission
To provide industrail manufacturers with an open-source, simple, and secure management structrure for edge devices and applications that gurantees operational continuity. This allows organizations like Weber to declare operating system (Fedora IoT) version and application versions they want to run on an individual device or a whole fleet of devices. The product will roll out the target configuration to devices while maintaining highest standards of safety, regulatory compliance (NIS2), and ensuring zero-downtime operations for critical machinery. | To design and develop a secure, Rust-based edge orchestrator for Weber’s Edge IPC that enables near zero-downtime updates for both the operating system and application layers. Our mission is to implement a management agent that leverages Fedora IoT, bootc, and Podman to ensure system updates and reliability. We create a cloud containing a database, which manages edge device infromation, and the running and desired OS and application versions. Users should be able to create, read, update, and delete devices, device groups, OS, and application information.

## Product Glossary
Term | Definition
Edge Device/ Edge IPC | An industrial Inter-Process Communication (IPC) hardware asset deployed on the factory floor on which our project runs.
Edge Agent | The sytem component that is running on the Edge IPC and controlls Updates and Communication. This includes Orchestrator, Download manager, and Health checks
Orchestrator | The central, automated controller within the Edge Agent that coordinates the execution of all local update activities. It is responsible for executing the update cycle by interpreting the remote configuration, monitoring the local system status, and sequentially triggering download, verification, and installation workflows to align the physical device with the cloud's target state.
Device Identity | A unique identifier permanently bound to a physical Edge Device, derived directly from its onboard hardware.
Image | A complete representation of a software layer packaged as a containerized asset ready for deployment.
Download Manager | A component within the Edge Agent tasked with fetching the required state of OS and applications on the device from the Cloud.
Inventory Database | Database in the Cloud that stores all information of the Edge Device, Appcations, and OS Versions. On top of that it stores the current deployed and the required OS and application version for each Edge Device.
Rollback | An automated emergency recovery operation that instantly reverts an Edge Device to its previously functional Operating System Image or Application Stack upon a post-update health check failure.
Health Check | A set of automated local test scripts executed immediately after a system switch or reboot to verify the functional correctness of critical device services before confirming an update as successful.
Fleet | The total of all edge devices that are managed by one company/user.
Database | Central Database where information about Edge Devices is gathered. This includes but isnt limited to: OS version, Host Info, Tenant, Group
Tenant | The customer where the Edge Device and its associated machinery is located
Group | Edge Devices can be put into Groups so that they can be modified together. IP has envisioned different Groups like porduction, testing etc.
Cloud | Includes Invetory Database and APIs to communicate with which the user and Edge IPC can communicate.

## Sprint Goals
Sprint # | Sprint goal
1 | None
2 | None
3 | None
4 | Optional
5 | Enable OS update swapping
6 | Database interaction with the user and Edge IPC is enabled
7 | Enhance database functionality and logging
8 | Integration Testing and Test Environment
9 | Save device and application Logs in Database
10 | Provide Logs and Streaming for Users
11 | First Demo preperations
12 | Finalize Project and Demo preperation
13 | Prepare Handover
14
15

## Velocity Tracking
Sprint # | Story Points Realized
1 | 0
2 | 12
3 | 19
4 | 15
5 | 25
6 | 21
7 | 11
8 | 6
9 | 0
10 | 0
11 | 0
12 | 0
13 | 0
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 86 | 86 | 92
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 | None |  | 0 | 86 | 0 | 92
2 | None |  | 12 | 74 | 12 | 80
3 | None |  | 16 | 58 | 19 | 61
4 | Optional |  | 20 | 38 | 15 | 46
5 | Enable OS update swapping |  | 21 | 17 | 25 | 21
6 | Database interaction with the user and Edge IPC is enabled |  | 17 | 0 | 21 | 0
Features
1 | None
2 | None | Review different Linux Distros | 3 |  | 3
|  | Review Backup options | 2 |  | 2
|  | Setup shared dev environment | 2 |  | 2
|  | Review options for zero downtime update | 2 |  | 2
|  | Initialize SBOM and Software Architecture | 1 |  | 1
|  | Review how TPM can be used | 2 |  | 2
3 | None | HTTPS Download Manager | 3 |  | 3
|  | API Protocoll & Mock Cloud | 3 |  | 5
|  | Setup DCO & CI Pipeline | 3 |  | 5
|  | Edge IPC Orchestrator | 5 |  | 5
|  | Signature Verification | 2 |  | 1
4 | Optional | Setup Cargo Workspace | 2 |  | 2
|  | rpm-ostree OS Update Controller | 2 |  | 2
|  | Post-Update Health Checks | 5 |  | 3
|  | Containerized Image Delivery | 8 |  | 5
|  | Device Inventory MVP | 3 |  | 3
5 | Enable OS update swapping | Build Process Video | 2 |  | 2
|  | Orchestrator check for update | 3 |  | 5
|  | Application Stack Controller | 3 |  | 5
|  | Refactor: bootc wrapper | 3 |  | 3
|  | rpm-ostree OS Update Controller | 2 |  | 2
|  | Update Documentation and Architecture | 3 |  | 3
|  | Setup Inventory Database | 5 |  | 5
6 | Database interaction with the user and Edge IPC is enabled | Create Scheme for Database and API calls | 3 |  | 3
|  | Refactor: Orchestrator initiates updates | 3 |  | 5
|  | Edge IPC to Cloud API for Database updates | 3 |  | 3
|  | User to Cloud API for Database Updates | 3 |  | 5
|  | Setup demo review | 5 |  | 5
|  | Refactor: Folder strucuter | 1 |  | 1
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 117 | 117
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
7 | Enhance database functionality and logging |  | 15 | 102 | 11 | 106
8 | Integration Testing and Test Environment |  | 19 | 83 | 6 | 100
9 | Save device and application Logs in Database |  | 21 | 62 | 0 | 100
10 | Provide Logs and Streaming for Users |  | 16 | 46 | 0 | 100
11 | First Demo preperations |  | 16 | 30 | 0 | 100
12 | Finalize Project and Demo preperation |  | 15 | 15 | 0 | 100
13 | Prepare Handover |  | 15 | 0 | 0 | 100
Features
7 | Enhance database functionality and logging
|  | Refactor: Introduce DTO | 3 |  | 3
|  | OS Image creation of different versions | 3 |  | 2
|  | Add Heartbeats | 1 |  | 1
|  | Research: Timestamp for DB changes | 3 |  | 1
|  | Signature Verification of image delivery | 3 |  | 2
|  | Add paging to device/group/application information | 2 |  | 2
8 | Integration Testing and Test Environment
|  | Create test setup | 8 |  | progress
|  | Create Integration tests | 5 |  | progress
|  | Authentication for User API | 3 |  | 3
|  | Research: Solution for storing time sensitive data | 3 |  | 3
9 | Save device and application Logs in Database
|  | Provide device logging function for storing logs in database | 2 |  | in progress
|  | TPM-based Device Indentity Verification at Edge IPC-Cloud API | 5 |  | in progress
|  | Log timestamp and user information for database changes | 3 |  | in progress
|  | Monitor and Mange Podman Containers | 8 |  | in progress
|  | Create API for time sensitive data | 3 |  | in progress
10 | Provide Logs and Streaming for Users
|  | Store App Config in databse | 3
|  | Store Podman logs in database | 3
|  | Store Device Logs in Database | 2
|  | Stream device information for debugging | 5
|  | Stream Podman application logs | 3
11 | First Demo preperations
|  | Create Demo day slide | 2
|  | Create Demo video | 3
|  | Update Post-Booting Health checks | 3
|  | API for uploading TPM/ID pairs | 3
|  | App Config Injector env config/mount paths to App Stack Controller | 5
12 | Finalize Project and Demo preperation
|  | Create Final Demo in Cooperation with POs | 5
|  | Check Project running as inteded | 5
|  | Databse: Only show valid image+OS versions | 3
|  | Cloud Backend Containerization | 2
13 | Prepare Handover
|  | Finalize user, (technical) design, and build/deploy documentation | 2
|  | Update SBOM | 3
|  | Annotate Code | 2
|  | Create Handover Document for Weber | 5
|  | Cleanup Project | 3

## Final Project Burndown Chart
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
10
11
12
13
14
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done
All Acceptance criterias defined in the backlog item are met and verified
Work done is pushed to the Github repository
For each backlog item a branch is created
Pull requests are created for each branch
Pull requests are reviewed
Corresponding branches are merged
Software Bill of Materials in the planning document is updated if new dependencies were added
The Wiki Section/Documentation corresponding to the work done is updated
Unit tests are written for all new logic
All unit tests must pass successfully in the CI pipeline
Code passes cargo fmt (style) and cargo clippy (linting)
All Developers assigned to a backlog item must communicate and coordinate with each other to complete the task
All features merged into the main branch; the CI pipeline is "Green"
Release candidates with a working and meaningful update to the previous sprint is tagged
Previously established features must continue to work.
All automated tests and validation checks for the developed components pass without errors
A single-click deployment/flashable image for the selected hardware is available
User documentation (usage examples, configuration steps, expected outputs) is finalized and up to date
All open-source licenses are documented and compliant
A "Handover Document" for Weber is completed in the Wiki
The final release has been reviewed and approved by all project team members and the industry partner

## Documentation
Type | Link / reference

## Planning Poker
Last Name | First Name | Value
Auer | Katharina | 0 | 0 | OK
#REF! | #REF! | 0
#REF! | #REF!
#REF! | #REF!
#REF! | #REF! |  | 0 | No size
#REF! | #REF! |  | 1 | Trivial size
#REF! | #REF! |  | 2 | Small size
#REF! | #REF! |  | 3 | Medium size
#REF! | #REF! |  | 5 | Large size
|  |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value

## Bill of Materials
# | Context | Name | Version | License | Comment
1 | OS | Fedora Linux | 44 | MIT
2 | Language | Rust | 1.95.0 (latest stable) | MIT/Apache 2.0
3 | Rust Toolchain | rustc | 1.95.0 (latest stable) | MIT/Apache 2.0
4 | Rust Buildsystem | cargo | 1.95.0 (latest stable) | MIT/Apache 2.0
5 | Rust Standard library | rust-std | 1.95.0 (latest stable) | MIT/Apache 2.0
6 | Rust Security/Audit (Dev Process) | cargo-audit | 0.22.1 | MIT/Apache 2.0
7 | Runtime | Container Engine (TBD) | TBD | TBD
8 | Security | TPM (TBD) | TBD | TBD
9 | Update | A/B Update Framework (TBD) | TBD | TBD
11 | Publish Process | Github Actions | N/A | N/A
12 | Rust Package | config | 0.15.22 | MIT/Apache 2.0 | https://github.com/rust-cli/config-rs
13 | Rust Package | env_logger | 0.11.10 | MIT/Apache 2.0 | https://github.com/rust-cli/env_logger
14 | Rust Package | log | 0.4.29 | MIT/Apache 2.0 | https://github.com/rust-lang/log
15 | Rust Package | serde | 1.0.228 | MIT/Apache 2.0 | https://github.com/serde-rs/serde
16 | Rust Package | tokio | 1.52.1 | MIT | https://github.com/tokio-rs/tokio
17 | Rust Package | reqwest | 0.13.3 | MIT/Apache 2.0 | https://github.com/seanmonstar/reqwest
18 | Rust Package | anyhow | 1.0.102 | MIT/Apache 2.0 | https://github.com/dtolnay/anyhow
19 | Rust Package | futures-util | 0.3.32 | MIT/Apache 2.0 | https://github.com/rust-lang/futures-rs
20 | Rust Package | base64 | 0.22 | MIT/Apache 2.0 | https://github.com/marshallpierce/rust-base64
21 | Rust Package | Serde JSON | 1 | MIT/Apache 2.0 | https://github.com/serde-rs/json
22 | Rust Package | ed25519-dalek | 2.2.0 | BSD-3-Clause | https://github.com/dalek-cryptography/curve25519-dalek
23 | Rust Package | clap | 4.6.1 | MIT/Apache 2.0 | https://github.com/clap-rs/clap
24 | Rust Package | async-trait | 0.1 | MIT/Apache 2.0
25 | Rust Package | tracing | 0.1.44 | MIT
26 | Rust Package | sea-orm | 2.0.0-rc | MIT/Apache 2.0 | https://github.com/SeaQL/sea-orm
27 | Rust Package | jsonwebtoken | 10.4.0 | MIT | https://github.com/Keats/jsonwebtoken
28 | Rust Package | tss_esapi | 7.7.0 | Apache 2.0 | https://github.com/parallaxsecond/rust-tss-esapi